## FMEA
DRONE PROPULSION SYSTEM — FAILURE MODE AND EFFECTS ANALYSIS (FMEA)
Part Family: Drone Propulsion System ¦ Revision: A ¦ Date: 2026-06-05 ¦ Owner: Quality Engineering
ID | COMPONENT INFORMATION |  |  | FAILURE ANALYSIS |  | RISK ASSESSMENT (BEFORE) |  |  | CURRENT CONTROLS |  |  | RPN | RECOMMENDED ACTION |  | TARGET DATE | REVISED RISK (AFTER) |  |  |  | STATUS
ID | Subsystem | Component | Function | Failure Mode | Failure Effect | Severity (S) | Potential Cause | Occurrence (O) | Prevention Control | Detection Control | Detection (D) | RPN | Recommended Action | Action Owner | Target Date | Rev. Severity | Rev. Occurrence | Rev. Detection | Rev. RPN | Status
1 | Propulsion | Motor | Convert electrical energy to rotational thrust | Bearing seizure | Complete loss of motor rotation → vehicle crash | 9 | Insufficient lubrication / contamination during assembly | 5 | Assembly SOP with torque spec | End-of-line vibration test | 5 | 225 | Add bearing inspection step at motor install; specify grease type in BOM | QE-Torres | 2026-07-05 | 9 | 3 | 3 | 81 | Open
2 | Propulsion | Motor | Convert electrical energy to rotational thrust | Rotor imbalance | Excessive vibration → structural fatigue of mount bracket | 7 | Damaged or contaminated rotor blades during handling | 4 | Incoming visual inspection | End-of-line vibration signature check | 4 | 112 | Implement dynamic balance check at motor receiving inspection | QE-Patel | 2026-06-26 | 7 | 2 | 2 | 28 | In Progress
3 | Propulsion | Motor | Convert electrical energy to rotational thrust | Winding insulation failure | Electrical short → ESC shutdown → propulsion loss | 9 | Thermal cycling stress; manufacturing defect | 3 | Supplier IPC-A-610 cert required | Hi-pot dielectric test at EOL | 3 | 81 | Require 100% hi-pot test at supplier; add thermal shock screen | QE-Nguyen | 2026-06-19 | 9 | 2 | 2 | 36 | In Progress
4 | Propulsion | Motor | Convert electrical energy to rotational thrust | Motor overheating | Demagnetization → power loss; potential fire risk | 8 | Incorrect motor specified for duty cycle; blocked airflow | 4 | Thermal simulation in design review | Thermal imaging at end-of-line | 4 | 128 | Add thermal derating curve to motor spec; test at max load | QE-Torres | 2026-07-20 | 8 | 2 | 3 | 48 | Open
5 | Propulsion | Motor | Convert electrical energy to rotational thrust | Incorrect motor installed | Wrong thrust profile → flight control failure | 8 | Part number confusion on similar-looking variants | 3 | Part number label on motor | Visual check at installation | 5 | 120 | Implement barcode scan verification at motor installation station | QE-Brooks | 2026-06-15 | 8 | 1 | 2 | 16 | Complete
6 | Propulsion | Electronic Speed Controller | Regulate motor power via PWM | Firmware mismatch | Motor runs at wrong speed profile → unstable flight | 8 | Firmware version not validated against motor/FC combination | 5 | Firmware release notes reviewed at build | EOL motor spin-up test | 4 | 160 | Lock firmware version in build traveler; add version check to EOL script | QE-Osei | 2026-06-19 | 8 | 2 | 2 | 32 | In Progress
7 | Propulsion | Electronic Speed Controller | Regulate motor power via PWM | Thermal shutdown | Mid-flight power cutoff → crash | 9 | Inadequate heatsinking; ambient temperature exceeded spec | 4 | Thermal analysis at design stage | Thermal imaging at EOL | 4 | 144 | Add 10°C thermal margin to ESC mounting design; validate in thermal chamber | QE-Torres | 2026-07-05 | 9 | 2 | 3 | 54 | In Progress
8 | Propulsion | Electronic Speed Controller | Regulate motor power via PWM | Signal loss | Motor stops receiving throttle signal → vehicle drop | 10 | Wiring harness damage; connector vibration loosening | 4 | Wiring harness routing guidelines | EOL signal continuity test | 3 | 120 | Add locking connector on ESC signal line; vibration test at system level | QE-Patel | 2026-06-26 | 10 | 2 | 2 | 40 | In Progress
9 | Propulsion | Electronic Speed Controller | Regulate motor power via PWM | Solder joint failure | Intermittent / complete power loss | 7 | Poor wetting; thermal fatigue from power cycling | 4 | Supplier IPC-A-610 Class 3 required | X-ray inspection sample plan | 5 | 140 | Increase x-ray sample rate to 20%; add thermal cycle screen | QE-Nguyen | 2026-06-26 | 7 | 3 | 3 | 63 | Open
10 | Propulsion | Electronic Speed Controller | Regulate motor power via PWM | Incorrect calibration | Motor timing mismatch → efficiency loss / instability | 6 | Calibration step skipped or documented incorrectly | 3 | Calibration procedure in work instruction | EOL calibration verification | 3 | 54 | Add mandatory calibration step with pass/fail criteria to build traveler | QE-Brooks | 2026-06-12 | 6 | 2 | 2 | 24 | Complete
11 | Propulsion | Propeller | Generate thrust via aerodynamic lift | Crack | Blade separation → catastrophic imbalance → crash | 10 | Impact damage; material defect; fatigue from over-torque | 3 | Incoming visual inspection SOP | EOL vibration signature test | 4 | 120 | Add dye-penetrant inspection to receiving; torque limiter on installation tool | QE-Torres | 2026-06-19 | 10 | 2 | 2 | 40 | In Progress
12 | Propulsion | Propeller | Generate thrust via aerodynamic lift | Delamination | Loss of aerodynamic profile → thrust asymmetry | 8 | CFRP layup defect; moisture ingress during storage | 4 | Supplier process audit annually | Ultrasonic C-scan sample inspection | 5 | 160 | Add C-scan to receiving AQL plan for CFRP propellers; improve storage spec | QE-Osei | 2026-07-05 | 8 | 2 | 3 | 48 | Open
13 | Propulsion | Propeller | Generate thrust via aerodynamic lift | Incorrect pitch installed | Wrong performance curve → under/over thrust | 7 | Wrong part pulled from inventory; no pitch marking check | 4 | Part labeling standard | Visual check at assembly | 5 | 140 | Add pitch laser-etch marking; implement scan-to-verify at assembly | QE-Patel | 2026-06-15 | 7 | 2 | 2 | 28 | Complete
14 | Propulsion | Propeller | Generate thrust via aerodynamic lift | Loose attachment | Propeller detaches in flight → crash | 10 | Under-torque at installation; incorrect fastener | 2 | Torque spec in work instruction | Torque audit at EOL | 2 | 40 | Use torque-indicating fasteners; add torque verification to build record | QE-Brooks | 2026-06-12 | 10 | 1 | 1 | 10 | Complete
15 | Propulsion | Propeller | Generate thrust via aerodynamic lift | Surface damage | Drag increase → reduced endurance | 4 | Handling damage post-inspection | 3 | Handling guidelines in SOP | Visual inspection before installation | 4 | 48 | Add foam-lined storage trays; inspect immediately before installation | QE-Nguyen | 2026-06-19 | 4 | 2 | 3 | 24 | Open
16 | Propulsion | Motor Mount Bracket | Rigidly locate motor to airframe | Hole position out of tolerance | Motor misalignment → vibration → fatigue | 7 | Fixture wear; CNC program error | 5 | First article inspection (FAI) required | CMM inspection per AQL | 5 | 175 | Tighten AQL from 1.0 to 0.4 for hole position; add SPC on CNC fixture | QE-Torres | 2026-06-26 | 7 | 3 | 3 | 63 | In Progress
17 | Propulsion | Motor Mount Bracket | Rigidly locate motor to airframe | Crack at mounting feature | Structural failure → motor detachment → crash | 9 | Stress concentration; incorrect alloy; over-torque | 3 | FEA review in design; material cert required | 100% visual + dye-pen on critical features | 3 | 81 | Add stress-relief radius to design; specify 7075-T6 only in BOM | QE-Patel | 2026-06-19 | 9 | 2 | 2 | 36 | In Progress
18 | Propulsion | Motor Mount Bracket | Rigidly locate motor to airframe | Flatness failure | Poor motor contact → vibration transmission | 6 | Machining stress relief insufficient | 4 | Flatness spec on drawing | CMM flatness measurement | 3 | 72 | Add stress-relief annealing step to manufacturing router | QE-Nguyen | 2026-06-26 | 6 | 2 | 2 | 24 | Complete
19 | Propulsion | Motor Mount Bracket | Rigidly locate motor to airframe | Fastener interface wear | Loose motor over time → vibration increase | 5 | Insufficient thread engagement; wrong fastener grade | 4 | Fastener spec in BOM | Torque-off test at sample rate | 4 | 80 | Specify thread insert (Helicoil) for high-cycle fastener interfaces | QE-Brooks | 2026-07-05 | 5 | 2 | 3 | 30 | Open
20 | Propulsion | Motor Mount Bracket | Rigidly locate motor to airframe | Incorrect material lot | Wrong alloy → reduced strength margin | 8 | Material certs not verified at receiving | 3 | Supplier material cert required | PMI (positive material identification) sample | 5 | 120 | Add 100% PMI scan at receiving inspection for motor mount brackets | QE-Osei | 2026-06-19 | 8 | 2 | 2 | 32 | In Progress
21 | Propulsion | Wiring Harness | Transmit power and signal to motor/ESC | Connector not fully seated | Intermittent power/signal → erratic motor behavior | 8 | Assembly error; connector design requires high insertion force | 5 | Assembly SOP with seating verification | EOL continuity test | 4 | 160 | Add positive-lock connectors; add seating force verification to work instruction | QE-Torres | 2026-06-19 | 8 | 3 | 2 | 48 | In Progress
22 | Propulsion | Wiring Harness | Transmit power and signal to motor/ESC | Wire chafing | Short circuit → fire risk or power loss | 9 | Inadequate routing protection in high-vibration zones | 4 | Routing guidelines in design SOP | Visual inspection at final assembly | 5 | 180 | Add grommets/abrasion sleeves at all frame contact points; add to inspection checklist | QE-Patel | 2026-06-26 | 9 | 2 | 3 | 54 | Open
23 | Propulsion | Wiring Harness | Transmit power and signal to motor/ESC | Incorrect pinout | Motor runs in reverse or not at all | 7 | Wiring error; missing polarization feature | 3 | Pinout drawing on work instruction | Functional motor spin test at EOL | 3 | 63 | Add polarized connector shrouds; implement spin-direction check in EOL software | QE-Nguyen | 2026-06-15 | 7 | 1 | 2 | 14 | Complete
24 | Propulsion | Wiring Harness | Transmit power and signal to motor/ESC | Insulation damage | Potential short; degraded signal integrity | 7 | Handling damage; sharp edge contact | 4 | Handling SOP | Visual inspection at installation | 4 | 112 | Add insulation damage to receiving inspection AQL; improve packaging spec | QE-Brooks | 2026-06-26 | 7 | 2 | 3 | 42 | Open
25 | Propulsion | Wiring Harness | Transmit power and signal to motor/ESC | Intermittent connection | Random power loss → flight instability | 8 | Vibration-induced fretting; poor crimp quality | 5 | Crimp quality spec in supplier requirements | EOL vibration + continuity test | 4 | 160 | Add crimp pull-test to receiving inspection; specify vibration-resistant crimp termination | QE-Osei | 2026-07-05 | 8 | 3 | 2 | 48 | In Progress
26 | Propulsion | Battery Connector | Connect battery to power distribution | Voltage drop | Reduced power delivery → ESC brownout | 7 | High contact resistance; oxidation; undersized contact | 4 | Connector rated spec in BOM | Voltage drop test at EOL | 3 | 84 | Add contact resistance measurement to receiving AQL | QE-Torres | 2026-06-19 | 7 | 2 | 2 | 28 | In Progress
27 | Propulsion | Battery Connector | Connect battery to power distribution | Loose contact | Intermittent power → erratic flight behavior | 8 | Worn contact spring; incorrect mating cycle count exceeded | 4 | Mating cycle rating in connector spec | Manual wiggle test + EOL continuity | 5 | 160 | Add mating cycle tracker to battery swap log; replace connectors at spec limit | QE-Patel | 2026-06-26 | 8 | 3 | 3 | 72 | Open
28 | Propulsion | Battery Connector | Connect battery to power distribution | Thermal damage | Connector melts → fire or power loss | 9 | Current draw exceeds connector rating; poor heat dissipation | 3 | Connector ampacity spec in BOM | Thermal imaging at EOL under load | 3 | 81 | Uprate connector to next ampacity class; add thermal fuse in line | QE-Nguyen | 2026-06-19 | 9 | 2 | 2 | 36 | In Progress
29 | Propulsion | Battery Connector | Connect battery to power distribution | Reverse polarity risk | Battery connected backwards → immediate ESC/motor damage | 10 | Symmetric connector allows incorrect mating | 2 | Polarity labeling on connector and battery | Visual polarity check in work instruction | 4 | 80 | Replace with asymmetric keyed connector to physically prevent reverse polarity | QE-Brooks | 2026-06-12 | 10 | 1 | 1 | 10 | Complete
30 | Propulsion | Battery Connector | Connect battery to power distribution | Contamination at contact surface | Increased resistance → heating → degraded performance | 6 | Exposure to oils, dust, moisture in assembly environment | 4 | Cleanliness spec in assembly area | Visual inspection at assembly | 4 | 96 | Add connector cap/plug until mating; add cleaning step to assembly SOP | QE-Osei | 2026-06-26 | 6 | 2 | 3 | 36 | Open
31 | Propulsion | Fasteners | Mechanically secure propulsion components | Under-torque on critical joint | Joint loosens under vibration → component shift | 7 | Torque wrench not calibrated; SOP not followed | 4 | Calibrated torque tools; torque spec in SOP | Torque audit at final assembly | 3 | 84 | Add digital torque tool with data logging; flag out-of-spec torques in real time | QE-Torres | 2026-06-19 | 7 | 2 | 2 | 28 | In Progress
32 | Propulsion | Fasteners | Mechanically secure propulsion components | Wrong fastener grade installed | Insufficient clamp load → joint failure under load | 7 | Mixed inventory; no grade marking on small fasteners | 4 | Part number on fastener bags | Visual check at assembly | 4 | 112 | Implement kitting by job traveler; add grade stamp requirement to fastener spec | QE-Patel | 2026-06-26 | 7 | 2 | 3 | 42 | Open
33 | Propulsion | Thermal Interface Material | Conduct heat from ESC to heatsink | Incorrect thickness applied | Thermal resistance above design spec → overheating | 6 | Manual application variability; no thickness gauge used | 5 | TIM application procedure in work instruction | Thermal imaging at EOL | 4 | 120 | Add shim template for TIM application; add thickness check with feeler gauge | QE-Nguyen | 2026-06-19 | 6 | 3 | 3 | 54 | Open
34 | Propulsion | Thermal Interface Material | Conduct heat from ESC to heatsink | Dry-out / delamination over thermal cycles | Thermal resistance increases with age | 5 | Low-grade TIM material; exceeding max operating temp | 3 | TIM material spec requires thermal conductivity rating | Thermal test at qualification | 4 | 60 | Upgrade to phase-change TIM; add thermal cycle qualification test | QE-Brooks | 2026-07-05 | 5 | 2 | 3 | 30 | Open
35 | Propulsion | Wiring Harness | Transmit power and signal to motor/ESC | Over-length wire routing | Wire caught in rotating propeller → crash | 10 | No wire length specification; inconsistent assembly | 3 | Wire routing diagram in work instruction | Visual pre-flight inspection checklist | 3 | 90 | Add wire length to BOM; add wire-to-prop clearance check to EOL inspection | QE-Osei | 2026-06-12 | 10 | 2 | 1 | 20 | In Progress

## Top 10 Risks
TOP 10 RISK ITEMS BY RPN
Rank | ID | Component | Failure Mode | Severity | Occurrence | Detection | RPN | Recommended Action
1 | 1 | Motor | Bearing seizure | 9 | 5 | 5 | 225 | Add bearing inspection step at motor install; specify grease type in BOM | Open
2 | 22 | Wiring Harness | Wire chafing | 9 | 4 | 5 | 180 | Add grommets/abrasion sleeves at all frame contact points; add to inspection checklist | Open
3 | 16 | Motor Mount Bracket | Hole position out of tolerance | 7 | 5 | 5 | 175 | Tighten AQL from 1.0 to 0.4 for hole position; add SPC on CNC fixture | In Progress
4 | 6 | Electronic Speed Controller | Firmware mismatch | 8 | 5 | 4 | 160 | Lock firmware version in build traveler; add version check to EOL script | In Progress
5 | 12 | Propeller | Delamination | 8 | 4 | 5 | 160 | Add C-scan to receiving AQL plan for CFRP propellers; improve storage spec | Open
6 | 21 | Wiring Harness | Connector not fully seated | 8 | 5 | 4 | 160 | Add positive-lock connectors; add seating force verification to work instruction | In Progress
7 | 25 | Wiring Harness | Intermittent connection | 8 | 5 | 4 | 160 | Add crimp pull-test to receiving inspection; specify vibration-resistant crimp termination | In Progress
8 | 27 | Battery Connector | Loose contact | 8 | 4 | 5 | 160 | Add mating cycle tracker to battery swap log; replace connectors at spec limit | Open
9 | 7 | Electronic Speed Controller | Thermal shutdown | 9 | 4 | 4 | 144 | Add 10°C thermal margin to ESC mounting design; validate in thermal chamber | In Progress
10 | 9 | Electronic Speed Controller | Solder joint failure | 7 | 4 | 5 | 140 | Increase x-ray sample rate to 20%; add thermal cycle screen | Open

## RPN Summary
RPN SUMMARY BY COMPONENT
Component | # Failure Modes | Avg RPN (Before) | Max RPN | Avg RPN (After) | Risk Reduction %
Motor | 5 | 133.2 | 225 | 41.8 | 68.6%
Wiring Harness | 6 | 127.5 | 180 | 37.7 | 70.4%
Motor Mount Bracket | 5 | 105.6 | 175 | 37 | 65.0%
Battery Connector | 5 | 100.2 | 160 | 36.4 | 63.7%
Propeller | 5 | 101.6 | 160 | 30 | 70.5%
Electronic Speed Controller | 5 | 123.6 | 160 | 42.6 | 65.5%
Thermal Interface Material | 2 | 90 | 120 | 42 | 53.3%
Fasteners | 2 | 98 | 112 | 35 | 64.3%

## Scoring Guide
SEVERITY SCALE
Score | Level | Description
10 | Critical | Safety-critical vehicle failure; regulatory violation
9 | Critical | Mission failure; loss of all propulsion
7-8 | High | Major performance degradation; significant rework
4-6 | Moderate | Moderate performance loss; rework required
1-3 | Low | Minor issue; cosmetic; no functional impact
OCCURRENCE SCALE
Score | Frequency | Description
10 | Very High | > 1 in 10 units
7-9 | High | 1 in 20 – 1 in 10
4-6 | Moderate | 1 in 100 – 1 in 20
2-3 | Low | 1 in 1000 – 1 in 100
1 | Remote | < 1 in 10,000
DETECTION SCALE
Score | Ability | Description
10 | None | No current detection control
7-9 | Weak | Detection only after failure in field
4-6 | Moderate | Manual inspection with some chance of escape
2-3 | Strong | Automated in-process or EOL detection
1 | Very Strong | 100% automated detection; mistake-proofed